## feb2018
Technology Rediscovery, LLC
Invoice #	T3		Invoice Date
Page	1		Work Period Start	1 Feb 2018
			Work Period End	28 Feb 2018
			Invoice Due
			Pmt Control Code:	3000-1002
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	32.58	$1,140.42

		Subtotal		$1,140.42
		Invoice Total		$1,140.42

					Invoice #	T3		Invoice Date	12/30/99
					Page	2		Work Period Start	1 Feb 2018
					Work Period End	28 Feb 2018

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					1 Feb 2018	09:15	11:15	2.000	* Sorting out tab movement on action request page
					1 Feb 2018	12:45	14:30	1.750	* Sorting out navigation issues into the case management page
					2 Feb 2018	09:00	11:30	2.500	* Found bug in navigation system to Case manager / * Creating case management XHTML page / * Building event add panel group
					8 Feb 2018	10:15	11:30	1.250	* Starting work on Event integrator class
					8 Feb 2018	12:15	16:00	3.750	* Writing the entire EventIntegrator.java class: methods for event and eventcategory insert, update, delete, and retrieve lists / * Writing ViolationIntegrator with insert, update, delete, and lists / * Buiding the eventConfiguration.xhtml page for simple display of event categories and updating, inserting / * Debugging retrieval of eventcategories from DB: yucky error of “origination” saved as “originaion” in the postgres Type. Messed up by dropping cascade…
					9 Feb 2018	08:00	09:10	1.167	* Debugging and cleaning event type management page (now it’s good!) / * Fixing error in propertyuseType_propertyUseTypeID field / * Testing property and case management flow in system for next steps
					9 Feb 2018	09:20	12:30	3.167	* Building code violation insertion and editing and review page (big task) / * Meeting with Liz and Amanda about phase 2
					15 Feb 2018	14:00	15:00	1.000	* Building the violation submission page
					16 Feb 2018	08:45	11:15	2.500	* Debugging ViolationAddBB naming issue in faces.config / * Building connection to ViolationCoordinator / * Fleshing out the ViolationAdd.xhtml fields / * Fixing Martha’s computer by replacing power supply
					16 Feb 2018	12:20	15:15	2.917	* Completing the build of the violation add system / * Tons and tons of annoying debugging of the foreign key errors__ having code set elements and code elements was a terrible idea: very confusing. Ug! / * Working insertions of code enforcement case!
					20 Feb 2018	08:20	09:40	1.333	* Pulling up all violations by case / * Creating system for storing and loading default code set by user
					20 Feb 2018	10:45	11:45	1.000	* Debugging code violation issues on display of code violations by case / * Planning event and case phase control model / * Documentation consultation on Junit testing for the event lifecycle
					20 Feb 2018	12:30	14:15	1.750	* Building the code violatoin sub-pages / * Scanning for integration tools for the code violations
					22 Feb 2018	08:45	11:00	2.250	* Building updating pages for code violations
					23 Feb 2018	09:00	11:45	2.750	* Finishing up touches on the code violation edit system / * Researching message bundle procedures & testing / * Planning event-related lifecycle for logging changes in code violations / * Successfully debugging violation edits and automatic event generation!!
					23 Feb 2018	13:00	14:30	1.500	* Building and debugging event logging system
					0.000
					0.000
					0.000	* Build robust system for connecting system event categories in the DB with actual event processing in our event coordinator
					0.000
					0.000

					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					Total Hours	32.583

					TODOs

					High priority
					Labels on code element – making enforcable elements are wrong
					Loading propert tabs upon incremental form submission on action submission page
					Throw SQL exception when creating DB connection and deal with it in integrators
					Property Unit Integration
					Updates from CountySite
					Loading entire property list into new system

					Lower Priority
					Build: Delete functions in code alley
					Adjust sql script to change name of field in request form to “atKnownAddress” so “true” is more interpretable

## jan2018
Technology Rediscovery, LLC
Invoice #	T2		Invoice Date	16 Feb 2018
Page	1		Work Period Start	1 January 2018
			Work Period End	31 January 2018
			Invoice Due	16 March 2018
			Pmt Control Code:	3000-1001
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	112.17	$3,925.83

		Subtotal		$3,925.83
		Invoice Total		$3,925.83

					Invoice #	T2		Invoice Date	16 Feb 2018
					Page	2		Work Period Start	1 January 2018
					Work Period End	31 January 2018

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					1 Jan 2018	12:30	15:30	3.000	*Creating insert scripts for database testing & test municipality: CogLand / * Final pass corrections on database DDL script / * Tinkering with order of INSERT statements and testing foreign key system
					1 Jan 2018	16:00	17:00	1.000	* Beginning building the business objects in Java: / Property entity: done, CECase entity: done, CasePhase enum: done
					1 Jan 2018	19:00	20:45	1.750	* Building final set of business object entities in Java / User: done, EventType: done, Person: done, LogEntry: done
					1 Jan 2018	22:00	22:30	0.500	* Beginning interface design for the integration classes
					2 Jan 2018	13:45	16:00	2.250	* Building interfaces for integration classes: LogCoordinator: done, PersonCoordinator: done, UserCoordinator: done, ViolationCoordinator: done
					2 Jan 2018	19:30	21:15	1.750	* Writing integrator guts for CodeSource and creating Coordinator and / Integreator class object creation pathways / * Referencing ptrack case study for object creation procedures
					2 Jan 2018	21:45	23:45	2.000	* Creating CodeSource management page and testing the lifecycle / * Debugging error messages and Exception throwing chain from Integreators to JSF Pages
					3 Jan 2018	04:30	06:30	2.000	* SUCCESS! Code source stack up and working: Integreator, coordinator, backing bean, and JSF page, and graceful failing (mostly)
					3 Jan 2018	08:30	09:30	1.000	* Meeting with COG about system progress
					3 Jan 2018	10:00	15:00	5.000	* Building CodeElementType integreator, controller, and backing bean. / * Building CodeElementType jsf page and testing SQL inserts / * Debugging updatecodesource method behavior
					4 Jan 2018	00:15	03:15	3.000	* Finishing the CodeElementType process by debugging weird execute method / * Begin building CodeElement integrator and backing bean
					4 Jan 2018	08:15	10:15	2.000	* Meeting with Gary and Jesse & new emplyee about entering code / * Planning new schema for code-related DB tables based on meeting feedback
					4 Jan 2018	13:00	14:00	1.000	* Meeting with student team abou getting more coding support for project
					4 Jan 2018	20:15	22:30	2.250	* Rebuilding databae table creation scripts based on feedback / * Debugging SQL code for DB rebuild with updated tables for code management / * Debugging weird page redirect issues on code soruce creation, default values / * Completed code element type insert and proofing code element type form
					5 Jan 2018	13:00	16:00	3.000	* Frustrating building and attempted debugging of the CodeSet flow: pending
					6 Jan 2018	10:45	12:30	1.750	* Infruriating but successful debugging of p:commandButton component in PrimeFaces → Turns out the default behavior of the primefaces component uses ajax which was not reloading the page as desired. ajax=false! Boom!
					6 Jan 2018	13:15	15:00	1.750	* Cleaning up and further debugging of CodeSet management process / * CodeSets are now good to go with retrieve, update, and add
					7 Jan 2018	03:30	04:00	0.500	* Preparing CodeElement class for integrator implementation
					7 Jan 2018	15:30	17:30	2.000	* Designing CodeSet, EnforcableCodeElement, and CodeElement integration methods and object hierarchy---a very messy process
					10 Jan 2018	08:15	12:00	3.750	* Completing the EnforceableCodeElement pathway (Designing integration methods, wiring up backing beans, testing, debugging) / * Success: getting lookup of EnforcableCodeElements based on CodeSet selection. / * Investigation of JSF2.0 method for bean injection at the Session level: needing to workaround deprecated createValueBinding method with javax.el.ValueExpression
					10 Jan 2018	21:15	22:30	1.250	* Tinkering with Dependency Injection models for saving session objects, like the current CodeSet made up of EnforcableCodeElement objects
					11 Jan 2018	06:30	07:30	1.000	* More debugging of DI model and trying to access objects placed in Session Scope (and getting them into SessionScope)! Yikes!
					11 Jan 2018	08:15	10:00	1.750	* SUCCESS! SessionScoped backing bean successfully loaded with an active code set which can be retrieved by any other bean through a managed propery!
					11 Jan 2018	10:30	15:30	5.000	* Connecting existing pages through the internal dashboard / * Wiring up header links for internal navigation / * Building out code element management pages (wiring up code element list table to the element editor / * Degubbing navigation system / * Cleaning up codeSourceManage.xhtml with typos / * System testing: strange behavior with clicking in data table and selected item not getting slurped up by faces as expected
					11 Jan 2018	19:00	21:15	2.250	* Adding update functionality for CodeElements: Debugging strange behavior / With updating element types, debugging SQL UPDATE statement
					12 Jan 2018	20:20	21:20	1.000	* Building UI for EnforcableCodeElement: User adding CodeElement objects to CodeSets.
					13 Jan 2018	12:00	14:30	2.500	* Continuing CodeSetElement UI building: Built three-step insertion flow with data tables and commandButtons. / * Debugged selectItem list, debugged SQL insert on codeSetElement / * System testing, template adjustment, removing println()s for working stuff
					13 Jan 2018	19:00	20:30	1.500	* Fixing codeSetElementManage.xhtml to provide a list of code set elements regardless of the page that sent the user here / * Degugging strange commandLink behaviors on Dashboard / * Revisiting SessionManager creation lifecyle process
					13 Jan 2018	21:00	21:30	0.500	* Debugging strange link behavior from dashboard!
					14 Jan 2018	09:15	12:00	2.750	*Building dashboard skeleton and planning new page modules / * Creating personManage.xhtml and debugging search functionality, adding case-insensitive search capabilityes, fixing strange bug on Person fields.
					14 Jan 2018	12:30	15:00	2.500	* Creating very beautiful Person update form, debugging form styling, consulting documentation about h:panelGrid and h:panelGroup elements
					15 Jan 2018	14:45	15:30	0.750	* Picking away at person update bugs
					15 Jan 2018	15:45	19:15	3.500	* Fixing horrid LocalDateTime to java.util.Date conversions / * Refactoring code to not wipe out data in the DB on UPDATE operations (Yikes!) / * Testing personUpdate.xhtml for bugs and sqashing them (field lengths max, etc.)
					15 Jan 2018	23:00	00:00	1.000	* Building personAdd.xhtml and debugging the small hitch-ups in rolling out that page add entity page
					16 Jan 2018	11:15	14:00	2.750	* Debugging PersonManage.xhtml: only showing one person/row / * Adding delete functions to person management / * Getting the lay of the land wrt property search relics from first round / * Creating integrator utility method for Property from RS / * Adding action methods to BB for with and w/o muni-search
					16 Jan 2018	14:15	16:00	1.750	* Building propertySearch.xhtml, tinkering with ajax requests / * Debeugging truly strange behavior with references to backing beans (some sort of name change that didn’t get processed correctly and shot nullpointers) / * Tweaking search functionality and debugging field mapping
					16 Jan 2018	20:00	21:30	1.500	* Testing and sanding down propertyProfile.xhtml / * Building skeletons of the sections for PropertyProfile.xhtml: cases, people, units, action requests, and occupancy inspections
					16 Jan 2018	22:15	00:00	1.750	* Building propertyUpdate.xhtml which is a large form / * Degubbing form error and incorrectly thinking the error was a PrimeFaces bug
					17 Jan 2018	00:00	00:45	0.750	* Planning ideas for working with PropertyUseTypes: need more methods in PropertyIntegrator for this to look up a useTypeName by ID
					17 Jan 2018	11:15	13:15	2.000	* Building getProperty(int id) method in propertyIntegrator / * Building CaseIntegrator and wiring it up to the property retrieval system
					17 Jan 2018	13:25	16:00	2.583	* Revising the code enforcement action request to use tabs / * Getting silly stumped over not working command buttons (couldn’t see validation errors on other tabs) / * Learning how to change tabs using a JS function call in a command button / * Editing text on the action request page
					19 Jan 2018	08:45	12:00	3.250	* Working on the public action request page – implementing tab functionality and creating a dedicated method for property object generation on the integration layer (so we’re not loading complete Property objects for public)
					19 Jan 2018	12:45	16:00	3.250	* Wresting with the action submission form: almost there!
					21 Jan 2018	11:00	11:30	0.500	* Debugging ActionRequest insert method in ActionRequestIntegrator
					22 Jan 2018	11:30	15:15	3.750	* Continuing debugging of action request insert and testing / * Success! After tons of SQL debugging, I found a pesky comma error. Action request cycle is working—persons, requests, and retrieval all working / * Beginning design of the session information box
					22 Jan 2018	19:45	22:45	3.000	* Creating caseAdd.xhtml, CaseAddBB, caseManageBB, WorkflowBB, workflow.xhtml –skeletons only / * Fleshing out caseAdd.xhtml / * Frustrating debugging of navigation to caseAdd.xhtml (turns out putting the literal path string as the return value of action method worked! Crazy!)
					23 Jan 2018	08:40	12:00	3.333	* User add and update page and integration class / * Municipality add and update and integration class in prep for Case / * Building user adding and managing and updating pages / * debugging date-related issues in User Process
					23 Jan 2018	12:30	15:30	3.000	* Proofing and finishing up user add and update pages / * Writing revised login process flow, including authentication verification in the integrator. / * Workout out a more robust session-state saving bean approach
					23 Jan 2018	19:15	23:15	4.000	* Case integration: writing getCasebyMuni, getCaseByProp, getCasebyID / * Building case integration queries / * Streamlining application-level and session-level bean creation and access / * Building backing bean and JSF skeletons for case-violation integration =
					24 Jan 2018	06:00	07:30	1.500	* Preparing to push Beta to server: packing .war file, connecting to DO server, transferring war, wrestling with Glassfish to start the domain
					24 Jan 2018	08:00	09:30	1.500	*Pushing to server and running the initial review meeting: dumping postgres locally, wiping brain of postgres on server, inserted new DB brain
					26 Jan2018	08:15	09:45	1.500	* Debugging integration error behavior of action requests showing up in the data table without any data: Success! I was trying to pull the requests by looking up requests by public CC instead of the needed requestID. / * Wrote new method for Public CC lookup
					26 Jan2018	10:15	11:15	1.000	* Experimenting and coding up date intervals and date formatting so we can calculate number of days since X action, etc.
					26 Jan2018	12:00	13:00	1.000	* Building request management system
					0.000	* Debugging navigation and label issues from Wed morning meeting / * Investigating setting up sub-domain for codeenforcement.tcvcog.com
					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					0.000
					Total Hours	112.167

## dec2017
Technology Rediscovery, LLC
Invoice #	T1		Invoice Date	9 Jan 2018
Page	1		Work Period Start	1 December 2017
			Work Period End	31 November 2017
			Invoice Due
			Pmt Control Code:	3000-1000
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	TechnologyRediscovery LLC

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development / Performed by Eric Darsow	$35.00	79.50	$2,782.50

		Subtotal		$2,782.50
		Invoice Total		$2,782.50

					Invoice #	T1		Invoice Date	9 Jan 2018
					Page	2		Work Period Start	1 December 2017
					Work Period End	31 November 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					30 Nov 2017			15.750	Correction for hours not included in hours total in Nov 2017 / Includes hours worked on 25 Nov 2017 starting at 9:15 through 30 Nov / This was caused by a spreadsheet sum() formula that didn’t include rows added after sheet creation when additional space was needed
					1 Dec 2017	05:00	11:00	6.000	Pushing DDL script to server / Packaging and uploading .war file for java code to server / Configuring postgres on server: creating DB, loading DDL / Troubleshooting iptables firewall issues / Styling page with images, grey background / Creating navigation links / Meeting with staff and Pitcairn
					2 Dec 2017	01:15	03:15	2.000	Working out data storage for various “types” and investigating enum support in Postrgres and JDBC drivers / Firing up the old Python scripts from the capstone course in the Fall / Planning property transfer into database
					3 Dec 2017	09:15	10:45	1.500	Loading property data into the DB with python script from Daniel / Checking prototype HTMLDataTable module trying without PrimeFaces
					5 Dec 2017	05:00	06:00	1.000	Starting fancy styling of pages
					8 Dec 2017	08:00	11:00	3.000	Learning about and implementing basic templating system / Creating template and testing styling of templated text / Ironing out page redirect and general navigation cases
					8 Dec 2017	13:30	16:00	2.500	Navigation troubleshooting / Setting up Enum support for status monitoring
					15 Dec 2017	08:30	11:00	2.500	*Refactored DB connection code to use resource injection from the DB Connection Class into integrators through the backing bean utils / * Enum type practice and table planning
					15 Dec 2017	12:15	14:00	1.750	Building out enum support structures
					17 Dec 2017	21:00	23:00	2.000	Building Person integrator class / Design consideration: case and event and CEAction Request process
					18 Dec 2017	09:30	11:30	2	* Finishing building out methods in person integrator / * Researching data/time handling in postgres, JDBC, and JSF
					18 Dec 2017	21:30	23:30	2	* Debugging permissions issues in PostgreSQL / * Planning DB permissions and user roles in PostgreSQL
					19 Dec 2017	12:00	16:00	4	* Debugging date issues in code enforcement action submission form page / * More Date investigation / * Finish coding the Person Integrator class, icluding update and inserts / * Editing requestManagementBean to store Person objects in DB / * Debugging person type lookup code in JSF page for request submission
					19 Dec 2017	18:30	19:00	0.5	* Debugging enum lists in the dropdown menus
					19 Dec 2017	20:15	22:15	2.000	* Designing property search on the action request form / * Debugging action method calls from the JSF page to PropSearchBean
					Logging			20 Dec 2017	08:15	09:45	1.500	* Learning about AJAX calls and implementing a basic AJAX-enabled / Command button for submitting form data without full page reload
					DB Connection			20 Dec 2017	10:00	11:30	1.500	* Building property search functionality into actionReqest form with AJAX calls
					Resource Bundle			20 Dec 2017	17:00	19:00	2.000	* Wiring up municipality and property search functions on ActionRequest page / To backing beans and integration classes. / * Database creation script redesign and editing: type creation, table editing, etc.
					21 Dec 2017	08:15	11:30	3.250	* Design of case event model, case phase model, and event procesing / * Meeting with Liz and Amanda about specific phase and case event names / * Even type planning: do we use trees? Are there state cycles?
					21 Dec 2017	12:45	15:35	3.000	* Meeting with Gary about phase specific events and overall workflow process / * Building out the database creation script from old version from sys project / * Thinking through how to work with property units, case types, etc. / * Consulting postgres documentation about array types
					21 Dec 2017	20:00	21:15	1.250	*Designing Binary Large Object (Images and docs) BLOB procedure
					22 Dec 2017	06:45	07:30	0.750	* Database DDL script editing and table structure design
					22 Dec 2017	08:00	12:00	4.000	* Meeting with Greg from Swissvale about CE workflow / * Designing table scheme for code violations / * Creating foreign and primary key constraints in tables in DDL script / * Editing DDL script for caps consistency, key name consistency, etc. / * Commenting DDL script
					22 Dec 2017	12:30	02:00	1.500	* Finishing the DDL script for the foundation of the database script / * Troubleshooting various syntax errors in the script
					26 Dec 2017	18:30	19:30	1.000	* Loading new database schema into Sylvia for testing / * Creating table drop and insert scripts for dbv1
					29 Dec 2017	12:30	14:00	1.500	* Developing page message systems / * Designing java and JSF message template code and testing / * Studying JSF messaging documentation
					30 Dec 2017	14:00	15:30	1.5	* Planning database v1.0 polishing revision priorities
					30 Dec 2017	20:00	21:00	1	* Solidifying case phase processing cycle theoretically and programmatically
					30 Dec 2017	21:15	00:00	2.75	* Creating skeletons of the Coordinators, Business Objects, and Integrators
					31 Dec 2017	00:00	00:45	0.75	* Creating skeletons of the Coordinators, Business Objects, and Integrators
					31 Dec 2017	09:45	11:15	1.5	* Buidling citation and court system tables in master DDL script		* Organize License stuff / * Data management plan drafts
					31 Dec 2017	12:45	15:00	2.25	* Final passs through postgres DDL script for minor fixes / * Rebuilt DROP script to align with new DDL / * Trial builds and teardowns with updated DDLL: success—no error build!

					Total Hours	79.500

## nov2017
Eric Darsow, Technology Services
Invoice #	7		Invoice Date	8 December 2017
Page	1		Work Period Start	1 November 2017
			Work Period End	30 November 2017
			Invoice Due	8 Jan 2018
			Pmt Control Code:	2000-1007
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	43.25	$1,513.75

		Subtotal		$1,513.75
		Invoice Total		$1,513.75

					Invoice #	7		Invoice Date	8 December 2017
					Page	2		Work Period Start	1 November 2017
					Work Period End	30 November 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					3 Nov 2017	09:00	16:00	7.000	Postgresql setup on the server / Orientation to Java Prime Faces display technology
					17 Nov 2017	08:00	15:00	7.000	Building DB tables for the public request page / Troubleshooting PostgreSQL access issues / Proofing DDL scripts produced by datamodeler
					17Nov 2017	19:00	20:00	1.000	Editing DDL script for creating the mini-database rollout
					20 Nov 2017	12:00	14:00	2.000	Adding sequences for table IDs / Creating INSERT scripts for populating select options tables
					20 Nov 2017	19:30	22:30	3.000	Creating ActionRequestBean and the ActionRequest class to manage the data that the action request form is inputting
					21 Nov 2017	08:30	14:00	5.500	Quashing form data retrieval bug / Creating lookup lists for code enforcement action request
					21 Nov 2017	18:00	21:00	3.000	Troubleshooting Glassfish database connectivity issues / Attempting upgrade to Glassfish 5 / Creating database connectivity factory on my own since glassfish won’t update / Using connection factory to get data from postgres! :)
					22 Nov 2017	08:30	10:00	1.500	Prepping form styling for first show / Meeting with Liz and Amanda about Dec 1 Rollout
					22 Nov 2017	20:00	00:00	4.000	SQL INSERT statements for action request form / Debugging database update routes and logs / Major breakthrough testing!
					23 Nov 2017	04:45	05:15	0.5	Building navigation cases for action submitrequest
					23 Nov 2017	18:30	21:30	3	Troubleshooting recursive and endless call to backingBeanUtils class / Reviewing application design guidelines / Tinkering with navigation cases for movement away from action request page / Planning object instantiation process
					24 Nov 2017	12:00	13:15	1.25	Designing action request lifecycle and consulting documentation / Configuring git updates and backup
					24 Nov 2017	18:15	07:15	1	Writing action request retrieval SQL SELECT script
					24 Nov 2017	21:45	00:00	2.250	Adjusting DDL script for action request table / Preparing date/time interfaces with database and front end / Preparing SQL query tools such as resultsets, preparedsatements, etc.
					25 Nov 2017	01:30	02:45	1.250	Setting up field flow from integrator bean, to backing bean, to jsf / Planning data type transformations, experiementing with LocalDate and LocalDateTIme
					25 Nov 2017	09:15	10:15	1.000	DateTime implementation
					25 Nov 2017	12:45	15:30	2.750	Storing request in DB, creating routing path to extract reuquest / Breakthrough: Effectively got data into and out of postgres in object form / Troubleshooting SQL query issues / Dealing with Date headaches and putting that off til later
					25 Nov 2017	18:30	20:30	2.000	Creating the action request management table skelton! Very exciting. / Troubleshooting (unsuccessfully action listener errors for managing action requests
					26 Nov 2017	18:30	19:30	1.000	Enumeration design – class self-references for attaching cases to projects, etc.
					27 Nov 2017	15:00	16:00	1.000	Meeting with Amanda and Liz
					28 Nov 2017	23:00	00:00	1.000	Bug squashing on DB connection overflow issues
					30 Nov 2017	00:00	06:00	6.000	Refactoring code to only create one Postgres connection pool. / Refactoring to move SQL statements into their own methods / Syncing with best practices in Managed Bean creation / Building public code enforcement tracking portal
					30 Nov 2017	20:00	21:00	1.000	Prep for municpality meeting

					Total Hours	43.250

## oct2017
Eric Darsow, Technology Services
Invoice #	6		Invoice Date	3 November 2017
Page	1		Work Period Start	1 October 2017
			Work Period End	31 October 2017
			Invoice Due	3 December 2017
			Pmt Control Code:	2000-1006
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	10.50	$367.50

		Subtotal		$367.50
		Invoice Total		$367.50

					Invoice #	6		Invoice Date	3 November 2017
					Page	2		Work Period Start	1 October 2017
					Work Period End	31 October 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					20 OCT 2017	10:00:00 AM	02:00:00 PM	4.0	(At COG office) Exploring JSF 2.0 standards, calling consulting company, reviewing books, working through class design issues and the composition process
					27 OCT 2017	09:00 AM	03:30 PM	6.5	(At COG office) Configuring systems for new user interface system through / Javaserver primefaces

					Total Hours	10.500

## sep2017
Eric Darsow, Technology Services
Invoice #	5		Invoice Date	20 October 2017
Page	1		Work Period Start	1 September 2017
			Work Period End	30 September 2017
			Invoice Due	20 November 2017
			Pmt Control Code:	2000-1005
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	25.00	$875.00

		Subtotal		$875.00
		Invoice Total		$875.00

					Invoice #	5		Invoice Date	20 October 2017
					Page	2		Work Period Start	1 September 2017
					Work Period End	30 September 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities

					4 SEP 2017	05:00 PM	11:00 PM	6.000	Setting up login system
					7 SEP 2017	04:00 PM	07:30 PM	3.500	Degugging login issues
					8 SEP 2017	08:30 AM	11:00 AM	2.500	Configuring page navigation cases
					11 SEP 2017	08:00 PM	10:00 PM	2.000	Server rebuild on digital ocean—scrapping old and configuring new system
					12 SEP 2017	12:00 AM	03:30 AM	3.500	Glassfish configuration and install
					13 SEP 2017	08:00 AM	09:00 AM	1.000	meeting and consult on DB design
					26 SEP 2017	06:00 PM	09:00 PM	3.000	Glassfish Server and PostgreSQL setup on Digial Ocean server
					28 SEP 2017	04:00:00 PM	07:30:00 PM	3.5	Consult with project collaborator

					Total Hours	25.000

## aug2017
Eric Darsow, Technology Services
Invoice #	4		Invoice Date	22 September 2017
Page	1		Work Period Start	1 August 2017
			Work Period End	31 August 2017
			Invoice Due	22 October 2017
			Pmt Control Code:	2000-1004
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	21.75	$761.25

		Subtotal		$761.25
		Invoice Total		$761.25

					Invoice #	4		Invoice Date	22 September 2017
					Page	2		Work Period Start	1 August 2017
					Work Period End	31 August 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					2 AUG 2017	11:15:00 AM	01:00:00 PM	1.75	Creating layer schema for system
					3 AUG 2017	09:00 PM	11:00 PM	2.000	Backing bean – integration layer design
					7AUG 2017	12:30 AM	01:30 AM	1.000	Setting up UserCoordinator class and planning application layers
					22 AUG 2017	05:00 PM	10:30 PM	5.500	Designing the prototype login page and code enforcement action request page / These are mock-ups that are just the user interface (UI) and still need to be / Wired up to the java server code in the “back end”
					22 AUG 2017	11:30 PM	01:00 AM	1.500	Finishing CE action request form, project admin (planning, document org)
					23 AUG 2017	05:30 AM	07:30 AM	2.000	Property main page design and testing / System planning
					23 AUG 2017	10:00 AM	11:00 AM	1.000	Project coordination Meeting with COG
					28 AUG 2017	04:00 PM	11:00 PM	7.000	Building User Interfaces prototypes

					Total Hours	21.750

## july2017
Eric Darsow, Technology Services
Invoice #	3		Invoice Date	4 Aug 2017
Page	1		Work Period Start	1 July 2017
			Work Period End	30 July 2017
			Invoice Due	4 September 2017
			Pmt Control Code:	2000-1003
Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:	Ongoing Development work on the code enforcement database project

Item No.	Description	Hourly Rate	Quantity (Hours)	Extended Price
1	Database and web application development	$35.00	22.75	$796.25

		Subtotal		$796.25
		Invoice Total		$796.25

					Invoice #	3		Invoice Date	4 Aug 2017
					Page	2		Work Period Start	1 July 2017
					Work Period End	30 July 2017

					Detailed time log and development activity summaries
					Date	Time start	Time end	Total Time	Description of Activities
					1 JUL 2017	04:15 PM	06:00 PM	1.750	Coding base property search xhtml page and its managed bean back-end propertySearchBean.java / Debugging xhtml parsing by faces servlet: solution – check xhtml sources location in web.xml file
					1 JUL 2017	07:15 PM	08:30 PM	1.250	Debugging Postres access from within managed bean – starting background on Dependency injection
					12 July 2017	08:00 PM	09:30 PM	1.500	Debugging database connection in the connection managed bean. / Creating context dependency injection framework for database connection which will allow various / beans to get a connection to postgres through the same class
					12 July 2017	10:15 AM	12:30 AM	2.250	Troubleshooting scoping on property search bean: setting property search bean to @SessionScoped / Dealing with strange Weld bugs and Glassfish server restarting and debugging to eliminate / strange errors. Success: Loading DB table data into JSF page
					13 JULY 2017	07:45 AM	08:15 AM	0.500	Design page flow and diagram it; review the database diagram for flow details
					13 JULY 2017	07:00 PM	10:30 PM	3.500	Background planning of entity objects: property, case, event / Coding property bean; troubleshooting UIData and component issues for displaying DB info / Success: Creating a linked list of properties for display based on “LIKE” query of address field
					28 JULY 2017	02:00 PM	04:30 PM	2.500	Faces Pages schema prep and design background Research
					29 JULY 2017	06:00 PM	09:00 PM	3.000	Designing system schema with Java Server Faces design guide by Kito Mann
					29 JULY 2017	09:30 PM	10:45 AM	1.250	Navigation, backing bean, and configuration file background preparation
					31 July 2017	02:30:00 PM	03:00:00 PM	0.5	Reviewing client requirement updates document and conferencing with Liz
					31 July 2017	05:00:00 PM	06:00:00 PM	1	JSF backing bean design development (these are the chunks of code that create logic / That the user interacts with in the browser)
					31 July 2017	06:30:00 PM	08:15:00 PM	1.75	Backing bean design development study – writing utility classes, creating entity classes that make sense for the COG, etc.
					31 July 2017	10:00:00 PM	12:00:00 AM	2	Backing bean design and development study

					Total Hours	22.750

## invoice2June2017
Invoice #	2		Invoice Date	3 July 2017
			Work Period	Month of June 2017

Turtle Creek Valley COG Code Enforcement Database Build project

Payer:	Turtle Creek Valley Council of Governments
	2700 Monroeville Boulevard / Monroeville, PA 15146 / 412-858-5115

Payee:	Eric Darsow

Description of Activities:		Ongoing Development work on the code enforcement database project

Date	Time start	Time end	Total Time	Hourly Rate	Extended Amount
11 JUN 2017	10:15 PM	12:15 AM	2.000	$35.00	$70.00
12 JUN 2017	08:00 AM	09:30 AM	1.500	$35.00	$52.50
26 JUN 2017	05:30 PM	06:30 PM	1.000	$35.00	$35.00
27 JUN 2017	03:30 PM	07:30 AM	4.000	$35.00	$140.00
28 JUN 2017	08:30 AM	09:30 AM	1.000	$35.00	$35.00
29 JUN 2017	02:30 PM	05:00 PM	2.500	$35.00	$87.50
30 JUN 2017	07:00 AM	12:00 PM	5.000	$35.00	$175.00
		Total Hours	17.000	Invoice Total	$595.00

## timetracker1
Eric Darsow Time Tracker
Turtle Creek Valley COG Code Enforcement Database Build project

Date	Time start	Time end	Total Time	Description of Activities
04/12/17	04:30 PM	07:00 PM	2.500	Configuring netbeans on server / Organizing files / Setting up database users / File transfer from Heinz staging server
04/12/17	08:30 PM	10:00 PM	2.500	Troubleshooting Glassfish install: java libraries needed to be installed and configured
04/15/17	09:00 PM	10:00 PM	1.000	Sample configuration of glassfish server to test database connectivity

		Total Hours	6.000
		Hourly rate	$35.00
		Total fees	$210.00

## DatabaseDevelopmentTimeline
Turtle Creek Valley Council of Governments – Code Enforcement Database Development Project Timeline

			Total Hours:	288

Date	Day	Project	Phase/Tasks	Hours	Notes
5 June 2017	Mon	COG Database	Server & Database Setup and Connection	8	Hopefully over-estimated
6 June 2017	Tue	COG Database	Server & Database Setup and Connection	8	Hopefully over-estimated
7 June 2017	Wed	Carpentry Contracting
8 June 2017	Thu	COG Database	Data Migration from MS Access to PostgreSQL	8	Creating scripts for tasks
9 June 2017	Fri	Home Improvement Course Teaching & Prep
10 June 2017	Sat	Carpentry Contracting
11 June 2017	Sun	Carpentry Contracting
12 June 2017	Mon	CMU CREATE Lab: Fluency Project
13 June 2017	Tue	CMU CREATE Lab: Fluency Project
14 June 2017	Wed	CMU CREATE Lab: Fluency Project
15 June 2017	Thu	COG Database	Data Migration from MS Access to PostgreSQL	8	Project Progress Report 1: emailed to team
16 June 2017	Fri	Home Improvement Course Teaching & Prep
17 June 2017	Sat	COG Database	CE officer access portal – code development	8	Write code to talk to new database
18 June 2017	Sun	Technology Rediscovery Development
19 June 2017	Mon	COG Database	CE officer access portal – code development	8
20 June 2017	Tue	COG Database	CE officer access portal – code development	8
21 June 2017	Wed	COG Database	CE officer access portal – code development	8
22 June 2017	Thu	COG Database	CE officer access portal – code development	8
23 June 2017	Fri	Home Improvement Course Teaching & Prep
24 June 2017	Sat	Personal
25 June 2017	Sun	Personal
26 June 2017	Mon	COG Database	CE officer access portal – lab testing	8	Done at ECD workplace / Project Progress Report 2: emailed to team
27 June 2017	Tue	COG Database	Data reporting module development & testing	8
28 June 2017	Wed	COG Database	Data reporting module development & testing	8
29 June 2017	Thu	COG Database	Data reporting module development & testing	8
30 June 2017	Fri	Technology Rediscovery Development
1 July 2017	Sat	Personal
2 July 2017	Sun	Personal
3 July 2017	Mon	COG Database	On-site server install	8	ECD at COG Office / Project Progress Report 3: emailed to team
4 July 2017	Tue	Personal			Internal COG team only – CE Portal
5 July 2017	Wed	COG Database	Field Test Beta Version (v.0.1)		Internal COG team only – Reporting modules
6 July 2017	Thu	COG Database	Field Test Beta Version (v.0.1)	8
7 July 2017	Fri	Technology Rediscovery Development
8 July 2017	Sat	Personal
9 July 2017	Sun	Personal
10 July 2017	Mon	CMU CREATE Lab: Fluency Project
11 July 2017	Tue	CMU CREATE Lab: Fluency Project
12 July 2017	Wed	COG Database	CE officer access portal – bug quashing	8
13 July 2017	Thu	COG Database	Borough & Citizen portals – code development & testing	8	Based on any needed new meetings and old CMU team meetings
14 July 2017	Fri	COG Database	Borough & Citizen portals – code development & testing	8
15 July 2017	Sat	Personal
16 July 2017	Sun	Travel to MN
17 July 2017	Mon	Teach Kid-tech Summer camp: Roch, MN
18 July 2017	Tue	Teach Kid-tech Summer camp: Roch, MN
19 July 2017	Wed	Teach Kid-tech Summer camp: Roch, MN
20 July 2017	Thu	Teach Kid-tech Summer camp: Roch, MN
21 July 2017	Fri	Teach Kid-tech Summer camp: Roch, MN
22 July 2017	Sat	Teach Kid-tech Summer camp: Roch, MN
23 July 2017	Sun	Teach Kid-tech Summer camp: Roch, MN
24 July 2017	Mon	COG Database	Borough & Citizen portals – code development & testing	8
25 July 2017	Tue	COG Database	Borough & Citizen portals – code development & testing	8	Project Progress Report 4: emailed to team
26 July 2017	Wed	COG Database	Field Test Beta Version (v.0.1)		Borough & Citizen portals – field training & testing
27 July 2017	Thu	COG Database	Borough & Citizen portals – bug quashing	8
28 July 2017	Fri	Technology Rediscovery Development
29 July 2017	Sat	Personal
30 July 2017	Sun	COG Database	On-site server setup	8	At COG office
31 July 2017	Mon	COG Database	Staff Training on new system	8
1 August 2017	Tue	COG Database	Deploy Beta Version (v.0.1)
2 August 2017	Wed	COG Database	On-site support for Beta deployment	8	At COG office or in field as needed
3 August 2017	Thu	COG Database	On-site support for Beta deployment	8	At COG office or in field as needed
4 August 2017	Fri	Technology Rediscovery Development
5 August 2017	Sat	Personal
6 August 2017	Sun	CMU CREATE Lab: Fluency Project
7 August 2017	Mon	CMU CREATE Lab: Fluency Project
8 August 2017	Tue	COG Database	Feature building from Beta field testing	8	New features identified during the initial field testing are built here, not during Beta development. This keeps us on track for Beta deployment and allows us to assemble a logical order for the feature developments
9 August 2017	Wed	COG Database	Feature building from Beta field testing	8
10 August 2017	Thu	COG Database	Feature building from Beta field testing	8
11 August 2017	Fri	Technology Rediscovery Development
12 August 2017	Sat	Home Electronics System Development
13 August 2017	Sun	Home Electronics System Development
14 August 2017	Mon	Home Electronics System Development
15 August 2017	Tue	Home Electronics System Development
16 August 2017	Wed	Home Electronics System Development
17 August 2017	Thu	Home Electronics System Development
18 August 2017	Fri	Home Electronics System Development
19 August 2017	Sat	Home Electronics System Development
20 August 2017	Sun	Home Electronics System Development
21 August 2017	Mon	COG Database	Feature building sprint – testing	8
22 August 2017	Tue	COG Database	Feature building sprint – testing	8
23 August 2017	Wed	COG Database	On-site server setup	8
24 August 2017	Thu	COG Database	Field Test Version 1.0		Time with COG Staff, CE Staff, and Borough staff
25 August 2017	Fri	COG Database	Field Testing – Bug Quashing	8
26 August 2017	Sat	Technology Rediscovery Development
27 August 2017	Sun	Personal
28 August 2017	Mon	COG Database	Field Testing – Bug Quashing	8
29 August 2017	Tue	COG Database	On-site server setup	8
30 August 2017	Wed	COG Database	Deploy Version 1.0		At COG office or in field as needed
31 August 2017	Thu	COG Database	On-site support for v.1.0 deployment	8	At COG office or in field as needed
1 September 2017	Fri	COG Database	On-site support for v.1.0 deployment	8	At COG office or in field as needed
2 September 2017	Sat	Technology Rediscovery Development
3 September 2017	Sun	Personal
		{schedule to be determined by project needs}

## phases
Phase	Description	Task “size”	Status	Est. Start	Est. End	Date started	Date completed	Notes
1	User requirements study	large	DONE			1. Sep. 2016	1. Dec. 2016
2	PostgreSQL Database design	medium	DONE			1. Sep. 2016	1. Dec. 2016
3	Reporting system design (Laruen’s R scripts)	medium	DONE			1. Sep. 2016	1. Dec. 2016
4	Data migration initial plan and testing	medium	DONE			1. Sep. 2016	1. Dec. 2016
5	Platform search and research (Javaserver Faces chosen)	small	DONE	1. Feb. 2017		1. Jun. 2017	1. Aug. 2017
6	User interface prototype design and feedback from CE staff and muni staff	large	IN PROCESS	1. Aug. 2017	1. Sep. 2017
7	Wiring up the user interface components to the server Java code	large	Queued	1. Sep. 2017	30. Sep. 2017
8	Lab testing of UI and Java components	medium	Queued	20. Sep. 2017	10. Oct. 2017
9	System security design, implementation and testing	medium	Queued	10. Oct. 2017	31. Oct. 2017			Outside consultant
10	Final review from COG staff before data migration and field testing	small	Queued	1. Sep. 2017	10. Sep. 2017
11	System documentation and search for maintenance company	Large	Queued	10. Sep. 2017	20. Oct. 2017
12	Field test Beta version 1 with CE staff and municipalities	medium	Queued	10. Sep. 2017	20. Sep. 2017
13	Bug fixes, design changes, and system shifts based on field testing	medium	Queued	20. Sep. 2017	10. Oct. 2017
14	Final data migration and system deployment	small	Queued	10. Oct. 2017	20. Oct. 2017
15	Field review of beta deployment and begin Version 1.1	small	Queued	20. Oct. 2017	31. Dec. 2017			Squish time

## workProcessLog
Date	Work Task	Notes	Time (hrs)
Saturday, July 22, 2017

## todos
TODO	Complexity	Status

## budget
Billing Summary for COG Database Build Process

Item	Unit Amount	Hours	Extended
ECD 1	$35.00	6	$210.00
ECD Inv 2	$35.00	17	$595.00
ECD July	$35.00	22.75	$796.25
ECD Aug	$35.00	14.75	$516.25
September		25.00	$875.00
October		10.50	$367.50
November		43.25	$1,513.75
December		79.50	$2,782.50
Total for 2017		218.75	$7,656.25

January 2018	35	112.167	$3,925.83
February 2018	35	62	$2,170.00
March 2018	35
April 2018	35
May 2018	35
June 2018	35
July 2018	35
August 2018	35
September 2018

Project Total			$13,752.08